## Slide 1: Agile Talks
Welcome
sergiotaborda@zbra.com.br
2013-03-20

## Slide 2: Agile Talks
  Inception (Sérgio)
    Origin of Agile
    Principles of Agile
  Planning (Sérgio)
    Planning Concepts
    Practices Workshop (next week)
  Engineering (Fábio)
    Agile Engineering
    Agile Engineering Workshop

## Slide 3: Agile Talks
Inception
sergiotaborda@zbra.com.br
2013-03-20

## Slide 4: Contents
  Part I - Origins
    All things Agile
    Insights
    What Agile Is
    What Agile Is Not
  Part II – Planning
    Project Dimensions
    The Product Owner and the Product Team
    Elicitation and Grooming
    Size Estimation and the Planning Poker
    Stories, Tasks and Burndown
    Reviews

## Slide 5
Agile Origins
Part II

## Slide 6: All Things Agile
Unit Testing
Agile Modeling
Agile
Engineering
Practices
Test Driven Development
Design Patterns
Refactoring
Integration Testing
Feature Driven Development
Behavior
Driven Development
Continuous Integration
Shared Code Ownership
Pair Programing
Coding Standards
Document Late

## Slide 7: All Things Agile
Kanban
Lean
XP
Scrum
Agile Unified Process
Unified Process
Rational Unified Process
Agile Engineering
Practices
Waterfall
Adaptative Software Development
Clearroom
Crystal
TSP/PSP

## Slide 8
1950
1960
1970
1980
1990
2000
2010
1970 : E. A. Edmonds introduced an adaptive software development process
1957: Geral M Weinber “Iterative and Incremental Development: A Brief History”
1999: Jim Hightsmith creates Adaptive Software Development targeting RAD development
1999: Andrew Hunt publishes “Pragmatic Programmer”
1999: Kent Beck creates Extreme Programming
1995: Jim Coplien defines Pair Programming
1995: Larry Constantine talks about “Dynamic Duos”
199: Jeff de Luca devised Feature Driven Development with further development by Peter Coad and Jon Kern
1999: Martin Fowler conceptualizes Continuous Integration
2000: Robert “Uncle Bob” Martin starts organizing the reunion at “The Lodge”
2001: The Agile Manifesto is born
2002: Kent Beck creates Test Driven Design
2002 James Grenning porposes Planning Poker
2003 Mary and Tom Poppendieck create Lean Software Development
1990: Toyota creates Lean Manufacturing Process
1970 : Barry Boehm proposes Wideband Delphi
1986: Barry Boehm proposes Spiral Model of Software Development
1956:Herbert D. Benington introduces the Waterfall model
1988: Scott Schultz indtroduces de Timebox concept
1989: Ward Cunningham describes de CRC technique
1992: Alistair Cockburn develops Crystal Methods
1994: Jim Coplien remarks that Daily Meetings leads to Hyperproductiviity
2002: Scrum community introduces measure of Velocity
2008: The concept of Definition of Ready is introduced in the Scrum community
1986:: Takeuchi and Nonaka use the term Scrum for the first time
2009: Software Craftsmanship Manifesto is born
1995: Jeff Sutherland and Ken Schwaber develop Scrum
1995: The CHAOS report is published
Notes: The older reference to something agile like originated in 1957 with Gerald M. Weinberg, as quoted ( in Larman, Craig; Basili, Victor R. (June 2003). "Iterative and Incremental Development: A Brief History“ (http://en.wikipedia.org/wiki/Agile_software_development)
Time lines at http://setandbma.wordpress.com/2012/03/23/agile-history/
http://guide.agilealliance.org/timeline.html
http://prezi.com/am04ulpcipyt/scrumfluenca/

## Slide 9: Agile is not a Manifest
Manifest
Principles
Individuals and interactions over Processes and tools
Working software over Comprehensive documentation
Customer collaboration over Contract negotiation
Responding to change over Following a plan
Our highest priority is to satisfy the customer through early and continuous delivery of valuable software.
Welcome changing requirements, even late in development
Working software is delivered frequently
Business people and developers must work together daily throughout the project.
Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done.
The most efficient and effective method of conveying information to and within a development team is face-to-face conversation.
Working software is the primary measure of progress.
Agile processes promote sustainable development. The sponsors, developers, and users should be able to maintain a constant pace indefinitely.
Continuous attention to technical excellence and good design enhances agility.
Simplicity--the art of maximizing the amount of work not done--is essential.
The best architectures, requirements, and designs emerge from self-organizing teams.
At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behavior accordingly.

## Slide 10: Insights
A waterfall process is ill-suited for common software development
  Requires a cyclic process
  Requires an iterative process
Software is not like building a bridge
  Does not rely on predictive rules
  Requires an adaptive process
People are not drones
  Building Software is an intellectual endeavor
  Face-to-Face Communication works best

## Slide 11: Iterative vs Incremental
Iterative
Incremental

## Slide 12: Incremental
Each step is not deliverable as the value in the whole
If money runs out , nothing is usable
The customer forces termination by any means necessary

## Slide 13: Iterative
Each step is deliverable with different value
Each step is deliverable with different, increasing, value
If money runs out , a simpler version will run
The customer has return over investiment at any point

## Slide 14: Software is a Product
Project
Product
Is Limited in Time
  Money runs out
  Interest runs out
  Oportunity phases out
Short Term Objectives
  Objectives do not change
Responsability
  Project Manager
  Stearing Comitee
Delegatable
Is Endless
  It makes money
  Is a brand
  Its a payed investment
Long Term Objectives
  Objectives will change
Responsability
  Product Departament
  Marketing
  Finance
Not Delegatable

## Slide 15: Software is a Product
Evolution needs to be controlled by Product Development
  In the pivot figure of the Product Owner
  Product Owner has responsibility for the features and the results (ROI)
Product Evolution is based on observation of users
  Measures to guide decision and not gut feeling
  Features not used by users are not features
  You are not the user

## Slide 16: Traditional View
The Project is the Software and vice versa
The Project will end => The Software will end
  Money runs out
  Time to Market run out
The Software has components => The project can be split in “phases”
  Deliver in “working” parts
We sell a Project/Software and steer a Software/Project
Projects need documentation => Software needs documentation
The customer is always right. Do it.

## Slide 17: Agile View
The Software is a Product
The Product will never end
  Because it makes money
The Project is an endeavor
  To implement a part of the software
  The endeavor has an end, and can fail, the product doesn’t
We sell a Project and steer a Project
  The client steers a Product and ROI
The project needs documentation, not documents
The software needs the documentation the client needs
The customer is not always right, but always has a point. Listen.

## Slide 18: The Stage-Gate Process Control
Stage 1
Gate 1
Stage 2
Stage n
Gate 2
Gate n
...
A sequece of stages protected by gates
  At a stage actions are performed
  At a gate artifacts are controlled. If ok, move to next stage
For Software Stages normally are
  Inception, Development, Implementation, Test , Deliver
Stage-Gate Sequence can repeated (Iterative processes)
  Waterfall is an Iterative Stage-Gate with 1 iteration (do or die)
  (R)UP is and Iterative Stage-Gate with N iterations

## Slide 19: Deterministic vs Stochastic
H
A
B
H
A
B
Deterministic
P(B | A) = 1
H
A
B
H
A
C
Stochastic
P(B | A) = f(H)
Empirical
Process
Defined
Process
Notes: Num processo estocastico o resultado é determinado com uma probabilidade que depende do estado do sistema

## Slide 20: The Empirical Process Control
Measure
Inspect
Adapt
Continuous (Not Stage-Gate)
In every action , in every individual (Not comand and control)

## Slide 21: People Communicating
Document Late
  Documenting may be necessary, but it is produced after the software, not before.
  Software guiding documentation, not documentation guiding software
Small Teams
  Minimize the N(N-1) /2 Channels Problem (0, 1, 3 , 6 , 10, 15)
  Information radiators
Maximize Focus
  Remove distractions
    Bugs are distractions
    Messed code is a distraction
    Wrong requirements are a distraction

## Slide 22: What Agile Is
Measure
Inspect
Adapt
Searching
Interacting People
Empirical Process Control Model
Technical and Comercial
Using
Tends To

## Slide 23: What Agile Is
People making a product
Continuously Measuring
  Times - time to deploy, time to boot, time to create feature, time to maintain, etc..
  Sizes – size of team, size of scope,
  Quality Metrics – size of code, size of modules, number of modules, coupling , dependency, etc...
  Satisfaction – users use feature, users like feature, bugs, etc..
Continuously Inspecting
  The Quality (what the numbers mean)
  The Scope (what to do next)
  The Product (the objectives are being accomplished)
  The Software (the quality is there? It still works ?)
  The Process (is helping or annoying ?)
Continuously Incrementing Value
  Deliver Soon
  Deliver Often
  Deliver something more each time
Continuously Adapt
  Change what is not working
Repeat

## Slide 24: What Agile Is Not
The Absence of Requirements Elicitation
  Can be the absence of all-up-front elicitation
The Absence of Documentation
  Can be the absence of most documents (risk management)
  Can be the absence of imutable contracts (legal rights)
The Absence of Order
  A single process is being followed
  Well defined roles and responsabilities
Leissez-Faire
  The team is not abandoned
  The team is not independent
  The team is not responsable for business decisions
Notes: Leissez-Faire (Deixe Fazer) é um termo da economia que se refere a uma politica liberal em que o mercado deve ser livre de fazer o que quiser desde que não compita com certos direitos alheios (http://pt.wikipedia.org/wiki/Laissez-faire)

## Slide 25
Agile Planning
Part II

## Slide 26
Schedule
Scope
Cost
Quality
Project Dimensions
Notes: O triangulo de ferro (Iron Triangle) também conhecido como triângulo de ouro.

## Slide 27: Tradicional View
Define Scope, Schedule , Cost
  You can optimize two
Assume Quality is given
  If you do not trust them, create a Quality Assurance body
Assume the Scope is contractual and all Scope is necessary
Assume Scope will not change
  If it does annoy them with Change Requests
Assume Risc is controllable
  Create a Stearing Commitee.
Schedule
Scope
Cost
Quality
Notes: O triangulo de ferro (Iron Triangle) também conhecido como triângulo de ouro.

## Slide 28
Risc
Cost
Quality
Schedule
Value
Scope
Project Dimensions
Notes: 6 Project Dimensions (Prince2)

## Slide 29: Modern View
Mesure all variables with numbers
Define Schedule, Cost and Quality
Assume Scope will change
  Because it will
  Because Value will change
  Because Business Objectives will change
Risc is controlable if measurable
  Adjust Scope acordingly
Risc
Scope
Cost
Quality
Schedule
Value
Variable
Fixed
Notes: O triangulo de ferro (Iron Triangle) também conhecido como triângulo de ouro.

## Slide 30: Tradicional View
Target driven
  Target a Cost
  Target a Schedule
  Target a Scope
Stearing
  The target does not move
  You cannot go back
  You cannot abort
  The arrow cannot be moved by the Steering Commitee to another target on demand
Notes: O triangulo de ferro (Iron Triangle) também conhecido como triângulo de ouro.

## Slide 31: Agile View
Objective driven
  Target a Cost
  Target a Schedule
  Target a Quality
  Target an Objective
Navigation
  The target does move
  You can go back
  You can always abort
  The boat can be moved by the Steering Commitee to another target on demand

## Slide 32
Steering vs Navigating

## Slide 33: Dimensions in Agile : Schedule
Define
  Releases by Time to Market Dates
  Goals for Releases
  Dates and Duration of Releases
  Number of Sprints in Release
Measure
  Story Points per Sprint (Velocity)
  Story Points in Release / Minimum Velocity
Review Constantly
  Release Backlog Burndown

## Slide 34
Project
Release 1 (Version 1.1)
Sprint 1
Sprint 2
Sprint 3
Release 2 (Version 1.2)
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Software
Software
Project A
Project B
Project C

## Slide 35
Release 1
Sprint 1
Sprint 2
Sprint 3
Release 2
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Software

## Slide 36: Dimensions in Agile : Cost
Define
  Cost =
  Cost Per Release =
  Velocity = Story Points Burned per Sprint
Measure
  Focus Factor = Fixed Budget / Velocity
  Nº of Sprints Needed = Backlog Size / Velocity
  Cost =
Notes: Sprints are not immediate one after the other. The overhead is the cost when the sprint is not “on”

## Slide 37: Agile Contract
Customer collaboration over contract negotiation
  “over” not “instead”
  Contract is legally mandatory
  “Negotiation” comes from problems with promises made about schedule and scope, that do not exist in agile
Agile Contract
  Define an umbrella contract that defines the stakeholders involved and the general rules of engagement
    Does not define scope, or time limit
  Append “Service Orders” for an appropriated time period (1 Release , 2 Releases, etc..)

## Slide 38: Dimensions in Agile : Scope
Define
  By Creating Stories
  Putting Stories in Backlog
Measure
  Size in Story Points
Review Constantly
  Priority
  Dependency
  Value

## Slide 39
Epic / Theme
Story
Task
Backlog
*
*
*
Product Backlog
Release
Backlog
Sprint
Backlog
Impediments
Backlog
Impediment
Block
Defect
Defect Backlog
*

## Slide 40: Story Taxomony
S-123
5
200
As a hotel guest I want to reschedule my reservation, with no extra expense, in order to maintain interest in hotel services
Acceptance
The Guest must be logged in It is not possible to reschedule for a past date
The Guest can only change his reservation
Tamanho (SP)
Prioridade
500
Value
Identification
Description
Acceptance Criteria

## Slide 41: INVEST (in) Ready Stories
I – Independent
  One Story must not depend on others (decoupling)
N – Negotiable
  Not all stories are necessary
  Not all stories are ASAP
V – Valuable
  Must improve business ROI
  Must benefit the user in some aspect
E – Estimable
  Must be possible to estimate its size
S – Small / Simple
  As small and simple as possible to help implementation
T – Testable
  Must be verifiable by the user
  Better if can be automatically, and repeatedly, verified
Notes: Epics are exceptions to the estimable rule, maily because they are not ready

## Slide 42: Story Taxomony
S-123
8
200
As a hotel guest I want to reschedule my reservation, with no extra expense, in order to maintain interest in hotel services
Acceptance
The Guest must be logged in It is not possible to reschedule for a past date
The Guest can only change his reservation
500
Actor
Goal
Pre and Pos Conditions + Alternative Paths
Business Value

## Slide 43
Release 1
Sprint 1
Sprint 2
Sprint 3
Release 2
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Software
Product Backlog
Release Backlog
Release Backlog
Sprint Backlog
Sprint Backlog
Sprint Backlog
Sprint Backlog
Sprint Backlog
Sprint Backlog
Sprint Backlog

## Slide 44: The Story Size
Size is a new property not found in traditional environments
Size a measure of work
Size is used to estimate of “how big the story is” and not “how long is necessary to implement it”
Size is related to
  Definition of “Done”
    Needed documentation , quality , etc..
  Number of tasks necessary
  Difficulty of tasks necessary
  Complexity of Business Rules
Size is not a quantity of Risk, nor a quantity of Time

## Slide 45: Determine Story Point Meaning
Ideal Day
  1 SP = 1 Ideal Day for a Senior Developer
Relative Size
  N SP = Size of a Reference story or story group
  1 SP = Size of a story that is 1/N of the reference story
  Normally N = 5
Calculated Size
  Based on a cost methodology like Function Point Analysis, User Case Points, etc…
  This approach falls rapidly to an all-elicitation-up-front

## Slide 46: Goodhart’s Law
“When a measure becomes a target,
it ceases to be a good measure”
Do not use Story Points contractually
Story Points are an “internal” measure

## Slide 47: Dimensions in Agile :Quality
Define
  Definition of “Ready”
  Definition of “Done”
  Acceptance Criteria (global and per story)
  Adherence to Standards (User Experience, Coding, Documenting , etc…)
Measure from
  Size of Defect Backlog
  Automatic Metrics (Sonar)
Review Constantly
  Too many constrains make Velocity slow down
  Too few constrains make Defect Backlog bigger

## Slide 48: Quality Assurance
Experiments
Tests
Manual
  Crystalized
Low Reproducibility
Slow
  Integration
  Environment
  Data
Red-Green Cycle
  Correct or incorrect
  No degree of correctness
  Other Metrics are hard to include
Acceptance Criteria
  One single special case
  Focus on “happy path”
Automatic
  Organic Growth
High Reproducibility
Slow to Fast
  Depending on what to test
  Unit => Fast
  Integration => Slow
Red-Green Cycle
  Correct or incorrect
  With degree of correctness
  Includes Other Metrics
Acceptance Criteria
  All cases
  Include corner cases

## Slide 51: Dimensions in Agile : Value
Define
  Relative Scale between stories (Priority Scale)
  By Order in Backlog
Measure
  Benefit : how bad if removed [1 to 9]
  Penalty : how badly would be missed [1 to 9]
  Value = Benefit + Penalty
Review Constantly
  Attractiveness =
Notes: Attractiveness = v / (t + r) where v = Relative Value , t = Relative Size , r = Relative Risk
Relative Value = value of story / Sum value of Backlog
Relative Size = size of story / backlog size
Relative Risk = story’s risk / sum of backlog stories risk

## Slide 52: Dimensions in Agile : Risk
Define
  Risk Exposure = Probability x Loss
  Loss = Money, Time or Story Points
  Sources of Risk
    Story, Release, Project, Software
      Ex: Risk of Dependent Systems are incompatible during integration
    People, Scope, Quality, Cost, Schedule
      Ex: Risk of Team members dropping out
      Ex: Risk of incorrect calculations affecting company billing
Measure
  Size of Defects Backlog / Velocity (min)
  Size of Stories Blocked by Impediments in Implements Backlog
  Value of Stories Blocked by Impediments in Implements Backlog

## Slide 53: The Product Owner (PO)
Controls the Product
Mediates between
  Stakeholders and the Team
  Stakeholders and Stakeholders
Enriches the Product in order to optimize the Return On Investment
  The Gain / Cost / Time
The PO is not a project manager (PM). A product may need several different PM. The PO is the “teams custumer”
Notes: http://pt.wikipedia.org/wiki/Retorno_sobre_investimento
http://en.wikipedia.org/wiki/Return_on_investment

## Slide 54: Product Team
Is not the Dev Team. It’s the “arms” of the PO
May include business specialist and advisors
Focus on collecting information from stakeholders
  Product Usability, FAQ, Suggestions, Features not used
Focus on measuring stories Value
  Benefit, Penalty, Priority
Focus on getting the stories to “Ready” state
  Focus on creating acceptance criteria
  Corner Cases
  Business Model consistency (interaction of rules)

## Slide 55: Elicitation and Ready State
Stakeholders
Elicitation and Value Estimation
Product Backlog Grooming

## Slide 56: Backlog Grooming
Add Story
  Collect actors, objectives and acceptance
Remove Story
  Log reasons for removal
Split Story
  Transform one story in two or more stories
Merge Stories
  Transform a collection of stories in a single story
Prioritize Story
  Change relative story priority
Move story Between backlogs
  From Product backlog to Release Backlog
  From Release A to Release B

## Slide 57: Size Estimation
Product Backlog Gromming
Estimation

## Slide 58: Define Story Scale
Define Scale
  Fixed
  Discrete
Elicit Scope Size
  From Team
    Planning Poker
  From Requirements
    Points per ...
1
2
3
5
8
13
0
½
∞
?
20
40
100
π

## Slide 59: Planning Poker
Repeat for each story
  Product Owner explains story
  Team members can ask questions to PO
  Team members select size secretly
      No Anchoring , No Dialog
  Team members show selections simultaneously
    If the same number is selected that is the story size
    Else , members select size secretly again
      Team members show selections simultaneously
        If The same number is selected that is the story size
        Else, members with higher and lower points explain selections. Resume point 2.

## Slide 60: Estimate With Planning Poker
As a Hotel Guest I want to create a Reservation for a period of time. Receive confirmation by email
As an Hotel Clerk I want to list free Rooms in a range of dates, in order to create a VIP Reservation.
As an anonymous user I want to login providing my username and password.
As an anonymous hotel guest I want to create a login account, in order to manage my reservations.
As a hotel guest I want to access my room’s bill.

## Slide 61: Preparing a Release
Define Goals for the release
Define Number of Sprints
  This indirectly define schedule
Elicit stories that achieve the Goal
  Put them in the Release Backlog
Estimate Size (if absent)
Estimate Value (if absent)
(Re)Prioritize
  Move to next release if necessary
  Move to backlog if no release can be defined
Adjust Goal(s) if necessary (resume 3)

## Slide 62: Preparing a Sprint
PO Defines Goals for the Sprint
Team Defines Sprint Budget
  Justifications can be offered
PO adds stories to sprint until budget is reached
  Cannot explode budget
  PO revisits stories goals and acceptance criteria
PO adds slack stories
  2 or 3 points worth depending on sprint size and previous velocities
Notes: If the stories have been in the backlog for too long is best to do a planning poker and estimate sizes. This is necessary even more so if 1SP = 1 Ideal Day

## Slide 63: Sprint Budget
Consider Number of Team members
Consider Each members Allocation ( full time, part-time)
  Team members can work in other projects
  Consider vacations
  Consider personal matters (1 day off to see the doctor)
Consider previous Velocity
  Consider the velocity of previous sprints
  Consider the variation of velocities
  Do not consider using the best velocity (false optimism)

## Slide 64: Estimate Possible Velocity/Budget
When SP = 1 Ideal Day
  Consider how many developers
  Consider days in Period
  Consider time allocation (A , in days)
  Consider team member focus factor (F, in %)
    Normal : 6/8 (= productive hours / available hours)
  Possible Velocity = P *
When SP =/= 1 Ideal Day
  Run some sprint and measure the real Velocity
  Extrapolate the possible Velocity using the measurements

## Slide 65: Velocity and Focus Factor
Sprint Velocity – Sum of Sizes of the Stories marked “Done” at the end of a sprint
  Definition of “Done” is predefined before a sprint and influences the size of the story.
Sprint Budget – Quantity of Story Points the Team considers appropriated for the Sprint Backlog before it is defined
  Normally the Velocity of previous Sprint
Sprint Factor of Focus = Velocity / Budget
  Should be 100% or more.
  Less than 75% represents severe impediments

## Slide 66: Sprint Work Breakdown
  Team members break stories in tasks
  Each task containing a duration estimation in hours
  Each task virtually assigned to a team member
  Sum of all task durations initializes Burndown Chart
Sum all hours

## Slide 67: Kanban Board (Execution)
Sprint Stories
Notes: Kanban é japonês para “sinal” no sentido de “placa vísivel que significa algo”

## Slide 68: Task Taxomony
S-123
5
200
As a hotel guest I want to reschedule my reservation, with no extra expense, in order to maintain interest in hotel services
Acceptance
The Guest must be logged in It is not possible to reschedule for a past date
The Guest can only change his reservation
T-123-3
16 h
Create web page
Denis
Estimated time
What to do ?
Assigned to
Identification

## Slide 69: Burndown Chart (Execution)
Remaining Effort (hours)
Sprint Day (at end)
Notes: The burn down should not go up. This is a symptom of something wrong in the process

## Slide 70: Sprint Review
Teams shows software working
  According to acceptance criteria
  Team shows impediments
Product Owner marks stories as “Done”
  The stories not done go back to the top of the backlog
Measure Velocity
  Velocity = Sum of Size of Stories Done
Product Owner and Teams dialog about impediments
  Impediments are put in the Impediments Backlog

## Slide 71: Release Review
Product Owner and Stakeholders
  Dialog about Impediments backlog, Defect Backlog and new Stories
  Dialog about Sprint Velocity and estimations for future sprints and impacts on the Release
    Some grooming will be necessary at this point
  Establish stories for Sprint N+2
    The next sprint should already be prepared
    The Release Review should be one or more sprints ahead

## Slide 72: Final Notes
Agile is Adaptive, but not instantaneously Adaptive
  The time between when a story is created and implemented should be more that one sprint
Agile is not ad doc, go horse , cowboy style
  Involves measuring and using measurements to decide
  Measurements are often dynamic, on the spot or automated
Quality is the main drive of sustainability
  Value must be delivered often, but that is not possible if defects take all the space in the backlog
Agile is not easy
  PO must constantly communicate with Stakeholders, not only at the end of a sprint. The PO must be several step ahead of Team. Story supply must be permanent.
  Team should be self-managed and that is a cultural challenge

## Slide 73: References
Agile Estimation and Planning
  Mike Cohn Boehm, Richard Turner, Prentice Hall
Balancing Agile and Discipline
  Barry Boehm and Richard Turner – Addison-Wesley
Software Requirements
  Karl E. Wiegers , Microsoft Press
Software Requirement Patterns
  Stephen Withall, Microsoft Press
Agile Software Management with Scrum
  Ken Schwaber, Microsoft Press
CHAOS Report
  http://www.projectsmart.co.uk/docs/chaos-report.pdf
  http://www.csus.edu/indiv/v/velianitis/161/ChaosReport.pdf
Agile Science
  http://www.agilescience.org/

## Slide 74: References
Principle of Least Astonishment
  http://en.wikipedia.org/wiki/Principle_of_least_astonishment
The Clean Coder
  Robert C. Martin et al, Prentice Hall
The Pragmmatic Programmer: From Journeyman to Master
  Andrew Hunt, David Thomas, Addison-Wesley
What Does “Going Agile” Really Mean?
  http://www.solutionsiq.com/resources/agileiq-blog/bid/58901/What-Does-Going-Agile-Really-Mean
Which Factors Affect Software Projects Maintenance Cost More? http://www.ncbi.nlm.nih.gov/pmc/articles/PMC3610582/
Agile Principles http://agilemanifesto.org/principles.html